## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | 2195-swen-261-07-c dingos
Testing Team Name | Stephen Bosonac

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | SB;02/22/2020 | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Sign-in page, with a means to enter a player name. | Pass | SB;02/22/2020 | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
| Given that no one else is using my name when I enter my name containing at least one alphanumeric character and optionally spaces in the sign-in form and click the Sign-in button then I expect the system to reserve my name and navigate back to the Home page. | Pass | SB;02/22/2020 | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
| Given that I am on the Sign-in page when I enter a name that does not contain at least one alphanumeric character or contains one or more characters that are not alphanumeric or spaces and click the Sign-in button then I expect the system to reject this name and return the Sign-in page. | Pass | SB;02/22/2020 | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
| Given that someone else with my name has signed-in when I enter my name in the Sign-in form and click the Sign-in button then I expect the system to reject my sign-in and return the Sign-in page for me to try a different name. | Pass | SB;02/22/2020 | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | SB;02/22/2020 | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | SB;02/22/2020 | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | FA 02/24/2020 | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | FA 02/24/2020 | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | FA 02/24/2020 | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View as the White player. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | FA 02/24/2020 | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | FA 02/24/2020 | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | FA 02/24/2020 | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | FA 02/24/2020 | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Fail | FA 2/24/2020 - Board is oriented similar for both Players. Did not figure out method of implementing in time. Will move to Sprint 2 backlog. | Pass | RH 04/07/2020 Passed; board orientation works correctly, changes according to player's turn | Pass | RH 04/07/2020 Passed; board orientation works correctly, changes according to player's turn
As a Player I want to be able to jump my opponent's pieces so that I can gain an advantage over them. | Given I have one or more jump moves available when it is my turn then I must be forced to take one of the jump moves available. | Fail | N/A (Not implemented this sprint) | Pass | RH 04/07/2020 | Pass | RH 04/07/2020
| Give I have jumped over an opponent's piece when it is my turn and I have further jump moves available then my opponent's piece should be removed and my turn should continue. | Fail | N/A (Not implemented this sprint) | Pass | RH 04/07/2020 | Pass | RH 04/07/2020
| Given that I have one or more jump moves available when it is my turn then I must be forced to take one of the jump moves available. | Fail | N/A (Not implemented this sprint) | Pass | RH 04/07/2020 | Pass | RH 04/07/2020
As a Player I want to be able to move a single checker piece (once) to a legal position so that I can advance. | Given that it is my turn, when I move a piece to an invalid space, then I expect my move to not be accepted and my piece to return to its previous space. | Fail | N/A (Not implemented this sprint) | Pass | RH 04/07/2020 | Pass | RH 04/07/2020
| Given that it is my turn, when I move a piece to an valid space, then my piece should stay in that space. | Fail | N/A (Not implemented this sprint) | Pass | RH 04/07/2020 | Pass | RH 04/07/2020
| Given it is my turn when I move a Piece and hit submit then I expect my move to be catalogued. | Fail | N/A (Not implemented this sprint) | Pass | RH 04/07/2020 | Pass | RH 04/07/2020
| Given it is my turn when I have made a move then I expect my turn to be over. | Fail | N/A (Not implemented this sprint) | Pass | RH 04/07/2020 | Pass | RH 04/07/2020
As a Player, I would like to be able to Sign-Out of the game, so that I can leave. | **Given** that I have signed in **when** I see the home page, **then** I should see a means to sign out. | Fail | N/A (Not implemented this sprint) | Pass | FA - 4/8/2020 | Pass | SD; 4/13/2020
| **Given** that I have not signed out, **when** I click the sign-out link, **then** my name should be removed from the lobby. | Fail | N/A (Not implemented this sprint) | Fail | FA - Game is not properly removed. After player and opponent are removed from game, if selected again, the end game screen is still displayed. | Pass | SD; 4/13/2020
| **Given** that I have signed out, **when** I see the home page, **then** I should see the sign-in link again and be able to log back in. | Fail | N/A (Not implemented this sprint) | Pass | FA - 4/8/2020 | Pass | SD; 4/13/2020
As a Kinged Player I want to be able to move forward and backward so I can more easily capture opposing pieces. | **Given** that I have moved a normal piece **when** I reach the opponent's end of the board, **then** my piece will be kinged. | Fail | N/A (Not implemented this sprint) | Fail | N/A (Not implemented this sprint) | Pass | SD; 4/13/2020
| **Given** that my piece has reached the end of the board, **when** I have been kinged, **then** my piece visual should be updated. | Fail | N/A (Not implemented this sprint) | Fail | N/A (Not implemented this sprint) | Pass | SD; 4/13/2020
| **Given** that my piece has been kinged, **when** I try to make a backward move to a valid space, **then** my move should be accepted. | Fail | N/A (Not implemented this sprint) | Fail | N/A (Not implemented this sprint) | Pass | SD; 4/13/2020
| **Given** that my backward move has been accepted, **when** I try to move forward or backward, **then** my move should be accepted. | Fail | N/A (Not implemented this sprint) | Fail | N/A (Not implemented this sprint) | Pass | SD; 4/13/2020
As a Player I want to be able to capture all of my opponents pieces so that I can win the game. | **Given** that my opponent has only one piece left, **when** I capture their piece, **then** I should win the game and see a "You won" message. | Fail | N/A (Not implemented this sprint) | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
| **Given** that I have only one piece left, **when** my opponent captures my piece, **then** my opponent should win the game and I should see a "You lost" message. | Fail | N/A (Not implemented this sprint) | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
| **Given** that we have been notified of our win/loss status, **when** the game ends, **then** both players should be directed to the home page. | Fail | N/A (Not implemented this sprint) | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
As a Player I want to put my opponent's pieces in a position where they cannot move so I can be declared the winner. | **Given** that it is the beginning of my turn, **when** it is no longer possible for me to move, **then** I should lose the game and see a "You lost" message. | Fail | N/A (Not implemented this sprint) | Fail | N/A (Not implemented this sprint) | Pass | SD; 4/13/2020
| **Given** that it is the beginning of my opponents turn, **when** it is no longer possible for them to move, **then** I should win the game and see a "You won" message. | Fail | N/A (Not implemented this sprint) | Fail | N/A (Not implemented this sprint) | Pass | SD; 4/13/2020
| **Given** that we have been notified of our win/loss status, **when** the game ends, **then** both players should be directed to the home page. | Fail | N/A (Not implemented this sprint) | Fail | N/A (Not implemented this sprint) | Pass | SD; 4/13/2020
As a Player I want to be able to resign or forfeit so that I can leave if I have plans or my opponent is too difficult to defeat. | **Given** that I want to resign, **when** I press the resign button, **then** I should see a "You lost" message. | Fail | N/A (Not implemented this sprint) | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
| **Given** that my opponent wants to resign, **when** my opponent presses the resign button, **then** I should see a "You won" message. | Fail | N/A (Not implemented this sprint) | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
| **Given** that we have been notified of our win/loss status, **when** the game ends, **then** both players should be directed to the home page. | Fail | N/A (Not implemented this sprint) | Fail | FA - Both Players are not directed to the same screen. | Pass | SD; 4/13/2020
| **Given** this it is NOT my turn, **when** I press the resign button, **then** I should be able to resign from the game. | Fail | N/A (Not implemented this sprint) | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
| **Given** that I have made a valid move, **when** I back up my move, **then** I should be able to resign. |  |  |  |  | Pass | SD; 4/13/2020
| **Given** that I have already made a Move, **when** I press the resign button, **then** I should not be able to resign from the game. | Fail | N/A (Not implemented this sprint) | Pass | FA 4/2/2020 | Pass | SD; 4/13/2020
As an AI Player I want to move a single checker piece (once) to a legal position so that I can advance. | **Given** I am done with my turn **when** the turn changes to the AI player **then** I expect them to make a move. | Fail | N/A (Not implemented this sprint) | Fail | N/A (Not implemented this sprint) | Pass | SD; 4/13/2020
| **Given** the AI Player has made a move **when** their turn is over **then** I expect it to be my turn | Fail | N/A (Not implemented this sprint) | Fail | N/A (Not implemented this sprint) | Pass | SD; 4/13/2020
As an AI Kinged Player I want to be able to move forward and backward so I can more easily capture opposing pieces. | **Given** the AI Player has been "Kinged" **when** it is their turn **then** I expect them to be able to have King movement functionality. | Fail | N/A (Not implemented this sprint) | Fail | N/A (Not implemented this sprint) | Pass | SD; 4/13/2020
| **Given** it is the AI player's turn **when** they move a piece into the last row of the board **then** I expect them to be Kinged. | Fail | N/A (Not implemented this sprint) | Fail | N/A (Not implemented this sprint) | Pass | SD; 4/13/2020
As an AI Player I want to be able to jump my opponent's pieces so that I can gain an advantage over them. | **Given** the AI Player has a jump move available **when** they make a jump move **then** I expect the move to be registered. | Fail | N/A (Not implemented this sprint) | Fail | N/A (Not implemented this sprint) | Pass | SD; 4/13/2020
| **Given** the AI Player has made a jump move **when** the turn changes **then** I expect the piece jumped to be removed from the board. | Fail | N/A (Not implemented this sprint) | Fail | N/A (Not implemented this sprint) | Pass | SD; 4/13/2020
As an AI Player I want to be able to jump more than one of my opponents pieces so that I can be more efficient in winning the game. | **Given** the AI Player has made a jump move **when** there is another jump move available to the piece that was moved **then** I expect them to be able to make the move. | Fail | N/A (Not implemented this sprint) | Fail | N/A (Not implemented this sprint) | Pass | SD; 4/13/2020